## Parameters
Project: | Embedded Systems
Tasks |  | estimated effort(hours) | Participants |  | Budget
Task1 | Sprint Planning |  | Serkan Efe Durusu | Serkan Efe Durusu | 1900-01-04 20:00
Task2 | Daily Scrum |  | Ismail Elmasry | Ismail Elmasry | 1900-01-04 20:00
Task3 | Sprint Review |  | can Işmar | can Işmar | 1900-01-04 20:00
Task4 | Sprint Retrospective |  | Marios Papalouka | Marios Papalouka | 1900-01-04 20:00
Task5 | Lectures/Plenary meetings |  | Metehan Topaç | Metehan Topaç | 1900-01-04 20:00
Task6 | Sprint Tasks | 1900-02-03 | Celine Zanders | Celine Zanders | 1900-01-04 20:00
Task7 | Sprint Task 1.1: Read course material
Task8 | Sprint Task 1.2: Feedback on example paper
Task9 | Sprint Task 1.3: Create schedule |  |  | Total budget | 1900-02-03
Task10 | Sprint Task 1.4: Description Document
Task11 | Sprint Task 1.5: Planning Document
Task12 | Sprint Task 1.6: Product backlog
Task13 | Sprint Task 2.1 designing a conceptual robot
Task14 | Sprint Task 2.2 Logic
Task15 | Sprint Task 2.3: Internet connectivity
Task16 | Sprint Task 2.4: UML diagrams
Task17 | Sprint Task 2.5: Midterm Presentation
Task18 | Sprint Task 2.6: Midterm video
Task19 | Sprint Task 3.1 Intermediate peer review
Task20 | Sprint Task 3.2 Acceptance Test Plan
Task21 | Sprint Task 3.3 User Manual
Task22 | Sprint Task 4.1 App implementation
Task23 | Sprint Task 4.2 Final Presentation
Task24 | Sprint Task 4.3 Acceptance Test
Task25 | Sprint Task 4.4 Gathering and submitting
Task26 | Sprint Task: building robot
Task27
Task28
Task29
Task30
Task31
Task32
Task33
Task34
Task35
Task36
Task37
Task38
Task39
Task40
Task41
Task42
Task43
Task44
Task45
Task46
Task47
Task48
Task49
Task50
Task51
Task52
Task53
Task54
Task55
Task56
Task57
Task58
Task59
Task60
Task61
Task62
Task63
Task64
Task65
Task66
Task67
Task68
Task69
Task70
Task71
Task72
Task73
Task74
Task75
Task76
Task77
Task78
Task79
Task80
Task81
Task82
Task83
Task84
Task85
Task86
Task87
Task88
Task89
Task90
Task91
Task92
Task93
Task94
Task95
Task96
Task97
Task98
Task99
Task100
Task101
Task102
Task103
Task104
Task105
Task106
Task107
Task108
Task109
Task110
Task111
Task112
Task113
Task114
Task115
Task116
Task117
| total estimated effort | 1900-02-03
| remaining budget: | 0
Formulas:
estimated effort(hours) = G13-SUM(C5:[estimated effort(hours), row above])
estimated effort(hours) = G13-[estimated effort(hours), row above]
Budget = SUM(G5:[Budget, row above])

## Serkan Efe Durusu
Tijdsregistratie | Serkan Efe Durusu
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
| Sprint Planning | 1:01
Daily Scrum
Sprint Review
Sprint Retrospective
| Lectures/Plenary meetings | 4:00 | 2:00 | 0.083333 | 0.083333
| Sprint Tasks | 2:00 | 3:00 | 0.125 | 0.41667
| Sprint Task 1.1: Read course material | 0.041667
Sprint Task 1.3: Create schedule
Sprint Task 1.4: Description Document
Sprint Task 1.5: Planning Document
Sprint Task 1.6: Product backlog
Sprint Task 2.1 designing a conceptual robot
Sprint Task 2.2 Logic
Sprint Task 2.3: Internet connectivity
Sprint Task 2.4: UML diagrams
Sprint Task 2.5: Midterm Presentation
Sprint Task 2.6: Midterm video
Sprint Task 3.1 Intermediate peer review
Sprint Task 3.2 Acceptance Test Plan
Sprint Task 3.3 User Manual
Sprint Task 4.1 App implementation
Sprint Task 4.2 Final Presentation
Sprint Task 4.3 Acceptance Test
Sprint Task 4.4 Gathering and submitting
Sprint Task: building robot
0
0
0
0
| Total | 0.33403 | 0.20833 | 0.20833 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
| hours spent | 0.33403 | 0.54236 | 0.75069 | 1899-12-31 06:01 | 1899-12-31 06:01 | 1899-12-31 06:01 | 1899-12-31 06:01 | 1899-12-31 06:01 | 1899-12-31 06:01 | 1899-12-31 06:01
| remaining hours | 1900-01-04 11:59 | 1900-01-04 06:59 | 1900-01-04 01:59 | 1900-01-03 13:59 | 1900-01-03 13:59 | 1900-01-03 13:59 | 1900-01-03 13:59 | 1900-01-03 13:59 | 1900-01-03 13:59 | 1900-01-03 13:59

## Ismail Elmasry
Tijdsregistratie | Ismail Elmasry
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
| Sprint Planning | 2:00 | 0:30 | 0.020833 | 0.020833
| Daily Scrum | 0:30 | 0.020833 | 0.020833 | 0.020833
| Sprint Review | 0:30
| Sprint Retrospective | 0:30 |  | 0.020833
| Lectures/Plenary meetings | 3:30 | 2:00 | 0.083333 | 0.083333
Sprint Tasks
| Sprint Task 1.1: Read course material | 0:30
Sprint Task 1.2: Feedback on example paper
| Sprint Task 1.3: Create schedule | 0:45
Sprint Task 1.4: Description Document
| Sprint Task 1.5: Planning Document | 2:00
| Sprint Task 1.6: Product backlog |  | 2:00
| Sprint Task 2.1 designing a conceptual robot |  | 4:00 | 5:00
Sprint Task 2.2 Logic
Sprint Task 2.3: Internet connectivity
Sprint Task 2.4: UML diagrams
| Sprint Task 2.5: Midterm Presentation |  |  |  | 0.083333
Sprint Task 2.6: Midterm video
Sprint Task 3.1 Intermediate peer review
Sprint Task 3.2 Acceptance Test Plan
Sprint Task 3.3 User Manual
Sprint Task 4.1 App implementation
Sprint Task 4.2 Final Presentation
Sprint Task 4.3 Acceptance Test
| Sprint Task 4.4 Gathering and submitting | 0:45 | 0:45 | 0:45 | 0:45
| Sprint Task: building robot |  |  |  | 0.25
0
0
0
0
| Total | 0.45833 | 0.40625 | 0.38542 | 0.48958 | 0 | 0 | 0 | 0 | 0 | 0
| hours spent | 0.45833 | 0.86458 | 1899-12-31 06:00 | 1899-12-31 17:45 | 1899-12-31 17:45 | 1899-12-31 17:45 | 1899-12-31 17:45 | 1899-12-31 17:45 | 1899-12-31 17:45 | 1899-12-31 17:45
| remaining hours | 1900-01-04 09:00 | 1900-01-03 23:15 | 1900-01-03 14:00 | 1900-01-03 02:15 | 1900-01-03 02:15 | 1900-01-03 02:15 | 1900-01-03 02:15 | 1900-01-03 02:15 | 1900-01-03 02:15 | 1900-01-03 02:15

## can Işmar
Time Registration | can Işmar
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
| Sprint Planning |  | 0:30 | 0:30
| Daily Scrum |  |  | 0:30
| Sprint Review | 1:00
Sprint Retrospective
| Lectures/Plenary meetings | 4:00 | 2:00 | 2:30
| Sprint Tasks | 3:00 | 1:00 | 1:00
Sprint Task 1.1: Read course material
Sprint Task 1.2: Feedback on example paper
Sprint Task 1.3: Create schedule
Sprint Task 1.4: Description Document
Sprint Task 1.5: Planning Document
Sprint Task 1.6: Product backlog
Sprint Task 2.1 designing a conceptual robot
Sprint Task 2.2 Logic
Sprint Task 2.3: Internet connectivity
Sprint Task 2.4: UML diagrams
Sprint Task 2.5: Midterm Presentation
Sprint Task 2.6: Midterm video
Sprint Task 3.1 Intermediate peer review
Sprint Task 3.2 Acceptance Test Plan
Sprint Task 3.3 User Manual
Sprint Task 4.1 App implementation
Sprint Task 4.2 Final Presentation
Sprint Task 4.3 Acceptance Test
| Sprint Task 4.4 Gathering and submitting | 0:30 |  | 0:30
Sprint Task: building robot
0
0
0
0
| Total | 0.35417 | 0.14583 | 0.20833 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| hours spent | 0.35417 | 0.5 | 0.70833 | 0.70833 | 0.70833 | 0.70833 | 0.70833 | 0.70833 | 0.70833 | 0.70833
| remaining hours | 1900-01-04 11:30 | 1900-01-04 08:00 | 1900-01-04 03:00 | 1900-01-04 03:00 | 1900-01-04 03:00 | 1900-01-04 03:00 | 1900-01-04 03:00 | 1900-01-04 03:00 | 1900-01-04 03:00 | 1900-01-04 03:00

## Marios Papalouka
Tijdsregistratie | Marios Papalouka
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
Sprint Planning
Daily Scrum
Sprint Review
Sprint Retrospective
| Lectures/Plenary meetings | 4:00 | 2:00 | 0.083333 | 0.083333
| Sprint Tasks | 2:00 | 3:00 | 0.16667 | 0.20833
| Sprint Task 1.1: Read course material | 1:00
Sprint Task 1.2: Feedback on example paper
Sprint Task 1.3: Create schedule
Sprint Task 1.4: Description Document
Sprint Task 1.5: Planning Document
Sprint Task 1.6: Product backlog
Sprint Task 2.1 designing a conceptual robot
Sprint Task 2.2 Logic
Sprint Task 2.3: Internet connectivity
Sprint Task 2.4: UML diagrams
Sprint Task 2.5: Midterm Presentation
Sprint Task 2.6: Midterm video
Sprint Task 3.1 Intermediate peer review
Sprint Task 3.2 Acceptance Test Plan
Sprint Task 3.3 User Manual
Sprint Task 4.1 App implementation
Sprint Task 4.2 Final Presentation
Sprint Task 4.3 Acceptance Test
Sprint Task 4.4 Gathering and submitting
Sprint Task: building robot
0
0
0
0
| Total | 0.29167 | 0.20833 | 0.25 | 0.29167 | 0 | 0 | 0 | 0 | 0 | 0
| hours spent | 0.29167 | 0.5 | 0.75 | 1899-12-31 01:00 | 1899-12-31 01:00 | 1899-12-31 01:00 | 1899-12-31 01:00 | 1899-12-31 01:00 | 1899-12-31 01:00 | 1899-12-31 01:00
| remaining hours | 1900-01-04 13:00 | 1900-01-04 08:00 | 1900-01-04 02:00 | 1900-01-03 19:00 | 1900-01-03 19:00 | 1900-01-03 19:00 | 1900-01-03 19:00 | 1900-01-03 19:00 | 1900-01-03 19:00 | 1900-01-03 19:00

## Metehan Topaç
Tijdsregistratie | Metehan Topaç
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
| Lectures/Plenary meetings | 4:00
Sprint Task 1.1: Reading Study Guide
Sprint Task 1.2: Idea Generation
| Additional Meeting | 1:00
| Sprint Task 1.3: Research on L293D | 2:00
| Sprint Task 1.4: Filling Preliminary Rubric |  | 2:30
| Sprint Task 1.4: Circuit Diagram |  | 0.125
| Sprint Task 2.1: Material List |  |  | 0.020833
| Sprint Task 2.2: Material List v2 |  |  | 0.020833
| Sprint Task 2.3: Melody Report |  |  |  | 0.03125
| Sprint Task 2.4: Coding and configuring Raspberry Pi |  |  |  | 0.16667
Sprint Task: building robot
0
0
0
0
| Total | 0.29167 | 0.22917 | 0.041667 | 0.19792 | 0 | 0 | 0 | 0 | 0 | 0
| hours spent | 0.29167 | 0.52083 | 0.5625 | 0.76042 | 0.76042 | 0.76042 | 0.76042 | 0.76042 | 0.76042 | 0.76042
| remaining hours | 1900-01-04 13:00 | 1900-01-04 07:30 | 1900-01-04 06:30 | 1900-01-04 01:45 | 1900-01-04 01:45 | 1900-01-04 01:45 | 1900-01-04 01:45 | 1900-01-04 01:45 | 1900-01-04 01:45 | 1900-01-04 01:45

## Celine Zanders
Tijdsregistratie | Celine Zanders
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
Sprint Planning
Daily Scrum
Sprint Review
Sprint Retrospective
| Lectures/Plenary meetings |  | 2:00 | 0.083333
| Sprint Tasks |  | 2:00 | 0.14583
Sprint Task 1.1: Read course material
Sprint Task 1.2: Feedback on example paper
Sprint Task 1.3: Create schedule
Sprint Task 1.4: Description Document
Sprint Task 1.5: Planning Document
Sprint Task 1.6: Product backlog
Sprint Task 2.1 designing a conceptual robot
Sprint Task 2.2 Logic
Sprint Task 2.3: Internet connectivity
Sprint Task 2.4: UML diagrams
Sprint Task 2.5: Midterm Presentation
Sprint Task 2.6: Midterm video
Sprint Task 3.1 Intermediate peer review
Sprint Task 3.2 Acceptance Test Plan
Sprint Task 3.3 User Manual
Sprint Task 4.1 App implementation
Sprint Task 4.2 Final Presentation
Sprint Task 4.3 Acceptance Test
Sprint Task 4.4 Gathering and submitting
Sprint Task: building robot
0
0
0
0
| Total | 0 | 0.16667 | 0.22917 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| hours spent | 0 | 0.16667 | 0.39583 | 0.39583 | 0.39583 | 0.39583 | 0.39583 | 0.39583 | 0.39583 | 0.39583
| remaining hours | 1900-01-04 20:00 | 1900-01-04 16:00 | 1900-01-04 10:30 | 1900-01-04 10:30 | 1900-01-04 10:30 | 1900-01-04 10:30 | 1900-01-04 10:30 | 1900-01-04 10:30 | 1900-01-04 10:30 | 1900-01-04 10:30

## Totals
Totals and charts
| week1 | week2 | week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | Totals | % Finished
Sprint Planning | 0.29236 | 0.041667 | 0.041667 | 0.020833 | 0 | 0 | 0 | 0 | 0 | 0 | 0.39653
Daily Scrum | 0.020833 | 0.020833 | 0.041667 | 0.020833 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10417
Sprint Review | 0.0625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0625
Sprint Retrospective | 0.0625 | 0 | 0.020833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.083333
Lectures/Plenary meetings | 0.72917 | 0.41667 | 0.4375 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 20:00
Sprint Tasks | 0.39583 | #REF! | 0.47917 | 0.625 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
Sprint Task 1.1: Read course material | 0.22917 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
Sprint Task 1.2: Feedback on example paper | 0 | 0 | 0.020833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.020833
Sprint Task 1.3: Create schedule | 0.03125 | 0 | 0.020833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.052083
Study | 0 | 0 | 0 | 0.03125 | 0 | 0 | 0 | 0 | 0 | 0 | 0.03125
Sprint Task 1.5: Planning Document | 0.083333 | 0 | 0 | 0.16667 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25
Sprint Task 1.6: Product backlog | 0 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.083333
Sprint Task 2.1 designing a conceptual robot | 0 | 0.16667 | 0.20833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.375
Sprint Task 2.2 Logic | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Task 2.3: Internet connectivity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Task 2.4: UML diagrams | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Task 2.5: Midterm Presentation | 0 | 0 | 0 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0.083333
Sprint Task 2.6: Midterm video | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Task 3.1 Intermediate peer review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Task 3.2 Acceptance Test Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Task 3.3 User Manual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Task 4.1 App implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Task 4.2 Final Presentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Task 4.3 Acceptance Test | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Task 4.4 Gathering and submitting | 0.052083 | 0.03125 | 0.052083 | 0.03125 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16667
Sprint Task: building robot | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| week1 | week2 | week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | Totals
Serkan Efe Durusu | 0.33403 | 0.20833 | 0.20833 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 06:01
Celine Zanders | 0 | 0.16667 | 0.22917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.39583
can Işmar | 0.35417 | 0.14583 | 0.20833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70833
Marios Papalouka | 0.29167 | 0.20833 | 0.25 | 0.29167 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 01:00
Metehan Topaç | 0.29167 | 0.22917 | 0.041667 | 0.19792 | 0 | 0 | 0 | 0 | 0 | 0 | 0.76042
Ismail Elmasry | 0.45833 | 0.40625 | 0.38542 | 0.48958 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 17:45
0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| 1899-12-31 17:31 | 1899-12-31 08:45 | 1899-12-31 07:45 | 1899-12-31 11:30 | 0 | 0 | 0 | 0 | 0 | 0 | 1900-01-04 21:31
Formulas:
Totals = SUM([week1]:[week10])