## Parameters
Project: | Embedded Systems
Tasks |  | estimated effort(hours) | Participants |  | Budget
Task1 | Sprint Planning |  | Serkan Efe Durusu | Serkan Efe Durusu | 1900-01-04 20:00
Task2 | Daily Scrum |  | Ismail Elmasry | Ismail Elmasry | 1900-01-04 20:00
Task3 | Sprint Review |  | can Işmar | can Işmar | 1900-01-04 20:00
Task4 | Sprint Retrospective |  | Marios Papalouka | Marios Papalouka | 1900-01-04 20:00
Task5 | Lectures/Plenary meetings |  | Metehan Topaç | Metehan Topaç | 1900-01-04 20:00
Task6 | Sprint Tasks | 1900-02-03 | Celine Zanders | Celine Zanders | 1900-01-04 20:00
Task7 | Sprint Task 1.1: Read course material
Task8 | Sprint Task 1.2: Feedback on example paper
Task9 | Sprint Task 1.3: Create schedule |  |  | Total budget | 1900-02-03
Task10 | Sprint Task 1.4: Description Document
Task11 | Sprint Task 1.5: Planning Document
Task12 | Sprint Task 1.6: Product backlog
Task13 | Sprint Task 2.1 designing a conceptual robot
Task14 | Sprint Task 2.2 Logic
Task15 | Sprint Task 2.3: Internet connectivity
Task16 | Sprint Task 2.4: UML diagrams
Task17 | Sprint Task 2.5: Midterm Presentation
Task18 | Sprint Task 2.6: Midterm video
Task19 | Sprint Task 3.1 Intermediate peer review
Task20 | Sprint Task 3.2 Acceptance Test Plan
Task21 | Sprint Task 3.3 User Manual
Task22 | Sprint Task 4.1 App implementation
Task23 | Sprint Task 4.2 Final Presentation
Task24 | Sprint Task 4.3 Acceptance Test
Task25 | Sprint Task 4.4 Gathering and submitting
Task26 | Sprint Task: building robot
Task27 | Sprint Task 4.5: requesting parts
Task28 | Belt inspection:
Task29 | sprint Task 4.6: Fixing the robot manipulator 3D mesh
Task30 | Sprint Task: testing servo
Task31 | Sprint Task: building gripper
Task32 | Sprint Task: Building Pusher
Task33 | Installing SERVOS
Task34 | Testing robot functionality
Task35
Task36
Task37
Task38
Task39
Task40
Task41
Task42
Task43
Task44
Task45
Task46
Task47
Task48
Task49
Task50
Task51
Task52
Task53
Task54
Task55
Task56
Task57
Task58
Task59
Task60
Task61
Task62
Task63
Task64
Task65
Task66
Task67
Task68
Task69
Task70
Task71
Task72
Task73
Task74
Task75
Task76
Task77
Task78
Task79
Task80
Task81
Task82
Task83
Task84
Task85
Task86
Task87
Task88
Task89
Task90
Task91
Task92
Task93
Task94
Task95
Task96
Task97
Task98
Task99
Task100
Task101
Task102
Task103
Task104
Task105
Task106
Task107
Task108
Task109
Task110
Task111
Task112
Task113
Task114
Task115
Task116
Task117
| total estimated effort | 1900-02-03
| remaining budget: | 0
Formulas:
estimated effort(hours) = G13-SUM(C5:[estimated effort(hours), row above])
estimated effort(hours) = G13-[estimated effort(hours), row above]
Budget = SUM(G5:[Budget, row above])

## Serkan Efe Durusu
Tijdsregistratie | Serkan Efe Durusu | [6 empty] | week 7: extra meeting on Friday, due to no meeting on Monday+ testing code
week 3:I was ill, contacted study advisor, hence low hours
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
| review sprint planning | 1:01 |  |  |  | 0.0069444 | 0.0069444
| Online contact with groupmembers | 0.0069444 | 0.0069444 | 0.0069444 | 0.0069444 | 0.0069444 | 0.0069444 | 0.0069444
Daily scrum
| Sprint Retrospective | 0:30 |  | 0.020833 |  |  |  | 0.020833
| Lectures/Plenary meetings | 3:30 | 2:00 | 0.083333 | 0.083333 | 0.125 | 0.10417 | 0.052083
| Sprint Tasks |  | 3:00 | 0.125
| Sprint Task 1.1: Read course material | 0.041667
| Workshop/presentation/prep |  |  |  |  | 0.125
| svg/urdf robot, searching for way to animate robot and testing for simulation |  |  |  | 0.25 | [6 empty] | Remark: animating URDF gave a lot of trouble as most guides are for gazebo. I had to test with gazebo, webots, fusion360 which took a long time. Finaly I found an online site to run urdf code in, but browser says it wasn't a safe site.
| urdf robot |  |  |  | 0.1875
| URDF finalize design - change joints add gripper | [5 empty] | 0.083333
| dc motors coding and testing |  |  |  |  | 0.14583
| design slide for disks and building and testing | [5 empty] | 0.125
| start coding for pusher |  |  |  |  | 0.020833
| rpi output tunes research | 0.083333
| setup arduino software | [6 empty] | 0.020833
| coding for error leds | [6 empty] | 0.020833
| coding error handling | [6 empty] | 0.041667
| review with other group |  |  |  |  | 0.03125
| fixing timesheet | 0:10 | 0:05 | 0.0034722 | 0.0069444 | 0.010417 | 0.010417 | 0.010417
| Uploading files | 0:10 | 0:30 | 0.0069444 | 0.0069444 | 0.0069444 | 0.0069444 | 0.020833 |  |  |  | Remark: some weeks gave problems uploading hence higher hours in some weeks
| Extra group meeting 10-06 to test and finetune code on robot parts | [6 empty] | 0.22917
| putting code together | [6 empty] | 1:00
| building robot parts | [6 empty] | 0:30
Sprint Task 4.4 Gathering and submitting
Sprint Task: building robot
Sprint Task 4.5: requesting parts
Belt inspection:
sprint Task 4.6: Fixing the robot manipulator 3D mesh
Sprint Task: testing servo
| Total | 0.35486 | 0.23958 | 0.24653 | 0.54167 | 0.47917 | 0.34375 | 0.48611 | 0 | 0 | 0
| hours spent | 0.35486 | 0.59444 | 0.84097 | 1899-12-31 09:11 | 1899-12-31 20:41 | 1900-01-01 04:56 | 1900-01-01 16:36 | 1900-01-01 16:36 | 1900-01-01 16:36 | 1900-01-01 16:36
| remaining hours | 1900-01-04 11:29 | 1900-01-04 05:44 | 1900-01-03 23:49 | 1900-01-03 10:49 | 1900-01-02 23:19 | 1900-01-02 15:04 | 1900-01-02 03:24 | 1900-01-02 03:24 | 1900-01-02 03:24 | 1900-01-02 03:24

## Ismail Elmasry
Tijdsregistratie | Ismail Elmasry
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
| Sprint Planning | 2:00 | 0:30 | 0.020833 | 0.020833 | 0.020833 | 0.020833 | 0.020833
| Daily Scrum | 0:30 | 0.020833 | 0.020833 | 0.020833 | 0.020833 | 0:15 | 0.010417
| Sprint Review | 0:30 |  |  |  | 0.020833 |  | 0.020833
| Sprint Retrospective | 0:30 |  | 0.020833
| Lectures/Plenary meetings | 3:30 | 2:00 | 0.083333 | 0.083333 | 0.125 | 0.083333 | 0.083333
Sprint Tasks
| Sprint Task 1.1: Read course material | 0:30
Sprint Task 1.2: Feedback on example paper
| Sprint Task 1.3: Create schedule | 0:45
Sprint Task 1.4: Description Document
| Sprint Task 1.5: Planning Document | 2:00
| Sprint Task 1.6: Product backlog |  | 2:00
| Sprint Task 2.1 designing a conceptual robot |  | 4:00 | 5:00
Sprint Task 2.2 Logic
Sprint Task 2.3: Internet connectivity
Sprint Task 2.4: UML diagrams
| Sprint Task 2.5: Midterm Presentation |  |  |  | 0.083333
Sprint Task 2.6: Midterm video
Sprint Task 3.1 Intermediate peer review
Sprint Task 3.2 Acceptance Test Plan
Sprint Task 3.3 User Manual
Sprint Task 4.1 App implementation
Sprint Task 4.2 Final Presentation
Sprint Task 4.3 Acceptance Test
| Sprint Task 4.4 Gathering and submitting | 0:45 | 0:45 | 0:45 | 0:45 | 0:45
| Sprint Task: building robot |  |  |  | 0.25 |  |  | 0.125
| Sprint Task 4.5: requesting parts |  |  |  |  | 0.020833
| Belt inspection: |  |  |  |  | 0.020833
| sprint Task 4.6: Fixing the robot manipulator 3D mesh |  |  |  |  | 0.16667
| Sprint Task: testing servo | [5 empty] | 0.041667
| Sprint Task: building gripper | [5 empty] | 0.125
| Sprint Task: Building Pusher | [5 empty] | 0.083333 | 0.041667
| Installing SERVOS | [5 empty] | 0.083333
| Testing robot functionality | [6 empty] | 0.20833
| Total | 0.45833 | 0.40625 | 0.38542 | 0.48958 | 0.42708 | 0.44792 | 0.51042 | 0 | 0 | 0
| hours spent | 0.45833 | 0.86458 | 1899-12-31 06:00 | 1899-12-31 17:45 | 1900-01-01 04:00 | 1900-01-01 14:45 | 1900-01-02 03:00 | 1900-01-02 03:00 | 1900-01-02 03:00 | 1900-01-02 03:00
| remaining hours | 1900-01-04 09:00 | 1900-01-03 23:15 | 1900-01-03 14:00 | 1900-01-03 02:15 | 1900-01-02 16:00 | 1900-01-02 05:15 | 1900-01-01 17:00 | 1900-01-01 17:00 | 1900-01-01 17:00 | 1900-01-01 17:00

## can Işmar
Time Registration | can Işmar
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
| Sprint Planning |  | 0:30 | 0:30 | 0:30 | 0:30 |  | 0.020833 | 0.020833
| Daily Scrum |  |  | 0:30 | 0:30 | 0:30
| Sprint Review | 1:00
Sprint Retrospective
| Lectures/Plenary meetings | 4:00 | 2:00 | 2:30 | 3:30 | 2:00 |  | 0.083333 | 0.083333
| Sprint Tasks | 3:00 | 1:00 | 1:00 | 2:00 | 5:00 | 1:30 | 0.33333 | 0.5
Sprint Task 1.1: Read course material
Sprint Task 1.2: Feedback on example paper
Sprint Task 1.3: Create schedule
Sprint Task 1.4: Description Document
Sprint Task 1.5: Planning Document
Sprint Task 1.6: Product backlog
Sprint Task 2.1 designing a conceptual robot
Sprint Task 2.2 Logic
Sprint Task 2.3: Internet connectivity
Sprint Task 2.4: UML diagrams
| Sprint Task 2.5: Midterm Presentation |  |  |  | 0.083333
Sprint Task 2.6: Midterm video
Sprint Task 3.1 Intermediate peer review
Sprint Task 3.2 Acceptance Test Plan
Sprint Task 3.3 User Manual
Sprint Task 4.1 App implementation
Sprint Task 4.2 Final Presentation
Sprint Task 4.3 Acceptance Test
| Sprint Task 4.4 Gathering and submitting | 0:30 |  | 0:30 | 0:30
Sprint Task: building robot
Sprint Task 4.5: requesting parts
Belt inspection:
sprint Task 4.6: Fixing the robot manipulator 3D mesh
Sprint Task: testing servo
| Total | 0.35417 | 0.14583 | 0.20833 | 0.375 | 0.33333 | 0.0625 | 0.4375 | 0.60417 | 0 | 0
| hours spent | 0.35417 | 0.5 | 0.70833 | 1899-12-31 02:00 | 1899-12-31 10:00 | 1899-12-31 11:30 | 1899-12-31 22:00 | 1900-01-01 12:30 | 1900-01-01 12:30 | 1900-01-01 12:30
| remaining hours | 1900-01-04 11:30 | 1900-01-04 08:00 | 1900-01-04 03:00 | 1900-01-03 18:00 | 1900-01-03 10:00 | 1900-01-03 08:30 | 1900-01-02 22:00 | 1900-01-02 07:30 | 1900-01-02 07:30 | 1900-01-02 07:30

## Marios Papalouka
Tijdsregistratie | Marios Papalouka
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
Sprint Planning
Daily Scrum
Sprint Review
Sprint Retrospective
| Lectures/Plenary meetings | 4:00 | 2:00 | 0.083333 | 0.083333 | 0.083333
| Sprint Tasks | 2:00 | 3:00 | 0.16667 | 0.20833 | 0.16667
| Sprint Task 1.1: Read course material | 1:00
Sprint Task 1.2: Feedback on example paper
Sprint Task 1.3: Create schedule
Sprint Task 1.4: Description Document
Sprint Task 1.5: Planning Document
Sprint Task 1.6: Product backlog
Sprint Task 2.1 designing a conceptual robot
Sprint Task 2.2 Logic
Sprint Task 2.3: Internet connectivity
Sprint Task 2.4: UML diagrams
| Sprint Task 2.5: Midterm Presentation |  |  |  | 0.083333
Sprint Task 2.6: Midterm video
Sprint Task 3.1 Intermediate peer review
Sprint Task 3.2 Acceptance Test Plan
Sprint Task 3.3 User Manual
Sprint Task 4.1 App implementation
Sprint Task 4.2 Final Presentation
Sprint Task 4.3 Acceptance Test
Sprint Task 4.4 Gathering and submitting
Sprint Task: building robot
Sprint Task 4.5: requesting parts
Belt inspection:
sprint Task 4.6: Fixing the robot manipulator 3D mesh
Sprint Task: testing servo
| Total | 0.29167 | 0.20833 | 0.25 | 0.375 | 0.25 | 0 | 0 | 0 | 0 | 0
| hours spent | 0.29167 | 0.5 | 0.75 | 1899-12-31 03:00 | 1899-12-31 09:00 | 1899-12-31 09:00 | 1899-12-31 09:00 | 1899-12-31 09:00 | 1899-12-31 09:00 | 1899-12-31 09:00
| remaining hours | 1900-01-04 13:00 | 1900-01-04 08:00 | 1900-01-04 02:00 | 1900-01-03 17:00 | 1900-01-03 11:00 | 1900-01-03 11:00 | 1900-01-03 11:00 | 1900-01-03 11:00 | 1900-01-03 11:00 | 1900-01-03 11:00

## Metehan Topaç
Tijdsregistratie | Metehan Topaç
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
| Lectures/Plenary meetings | 4:00 | 2:00 | 0.083333 | 0.16667 | 0.083333 | 0.083333 | 0.083333
| Sprint Task 1.1: Reading Study Guide | 0.041667
| Sprint Task 1.2: Idea Generation | 0:30
| Additional Meeting | 1:00
| Sprint Task 1.3: Research on L293D | 2:00
| Sprint Task 1.4: Filling Preliminary Rubric |  | 2:30 |  | 0.041667 |  | 0.083333
| Sprint Task 1.4: Circuit Diagram |  | 0.125
| Sprint Task 2.1: Material List |  |  | 0.020833
| Sprint Task 2.2: Material List v2 |  |  | 0.020833
| Sprint Task 2.3: Melody Report |  |  |  | 0.03125
| Sprint Task 2.4: Coding and configuring Raspberry Pi |  |  |  | 0.16667
| Sprint Task 3.1: Work on simulation (Unity) |  |  |  | 0.125 | 0.20833
| Sprint Task 3.2: Simulation Update (Unity) | [5 empty] | 0.16667
| Sprint Task 4.1: Servo code for robot arm | [6 empty] | 0.125
| Sprint Task 4.2: Melody code assembly and Arduino memory problem | [6 empty] | 0.16667
| Sprint Task 4.3: Additional meeting for testing the code | [6 empty] | 0.29167
| Sprint Task 4.4: Merging the gripper code with servo code | [6 empty] | 0.083333
| Sprint Task 4.5: Work on servo code after the testing done in the additional meeting | [6 empty] | 0.125
| Sprint Task 4.6: Integrating switch code into arm code | [6 empty] | 0.10417
| Sprint Task 4.7: Research on how to fix memory problem of the arduino | [6 empty] | 0.20833
Sprint Task: building robot
Sprint Task 4.5: requesting parts
Belt inspection:
sprint Task 4.6: Fixing the robot manipulator 3D mesh
Sprint Task: testing servo
| Total | 0.35417 | 0.3125 | 0.125 | 0.53125 | 0.29167 | 0.33333 | 1899-12-31 04:30 | 0 | 0 | 0
| hours spent | 0.35417 | 0.66667 | 0.79167 | 1899-12-31 07:45 | 1899-12-31 14:45 | 1899-12-31 22:45 | 1900-01-02 03:15 | 1900-01-02 03:15 | 1900-01-02 03:15 | 1900-01-02 03:15
| remaining hours | 1900-01-04 11:30 | 1900-01-04 04:00 | 1900-01-04 01:00 | 1900-01-03 12:15 | 1900-01-03 05:15 | 1900-01-02 21:15 | 1900-01-01 16:45 | 1900-01-01 16:45 | 1900-01-01 16:45 | 1900-01-01 16:45

## Celine Zanders
Tijdsregistratie | Celine Zanders
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
Sprint Planning
Daily Scrum
Sprint Review
Sprint Retrospective
| Lectures/Plenary meetings | 4:00 | 2:00 | 0.083333 | 0.083333 | 0.16667 | 0.083333 | 0.052083
| Sprint Tasks | 0:30 | 2:00 | 0.14583 | 0.041667 | 0.0625 | 0.25 | 0.020833
| Sprint Task 1.1: Read course material | 0.020833
Sprint Task 1.2: Feedback on example paper
Sprint Task 1.3: Create schedule
Sprint Task 1.4: Description Document
Sprint Task 1.5: Planning Document
Sprint Task 1.6: Product backlog
Sprint Task 2.1 designing a conceptual robot
Sprint Task 2.2 Logic
Sprint Task 2.3: Internet connectivity
Sprint Task 2.4: UML diagrams
Sprint Task 2.5: Midterm Presentation
Sprint Task 2.6: Midterm video
Sprint Task 3.1 Intermediate peer review
Sprint Task 3.2 Acceptance Test Plan
Sprint Task 3.3 User Manual
Sprint Task 4.1 App implementation
Sprint Task 4.2 Final Presentation
Sprint Task 4.3 Acceptance Test
Sprint Task 4.4 Gathering and submitting
| Sprint Task: building robot | [6 empty] | 0.083333
Sprint Task 4.5: requesting parts
Belt inspection:
sprint Task 4.6: Fixing the robot manipulator 3D mesh
Sprint Task: testing servo
| Total | 0.20833 | 0.16667 | 0.22917 | 0.125 | 0.22917 | 0.33333 | 0.15625 | 0 | 0 | 0
| hours spent | 0.20833 | 0.375 | 0.60417 | 0.72917 | 0.95833 | 1899-12-31 07:00 | 1899-12-31 10:45 | 1899-12-31 10:45 | 1899-12-31 10:45 | 1899-12-31 10:45
| remaining hours | 1900-01-04 15:00 | 1900-01-04 11:00 | 1900-01-04 05:30 | 1900-01-04 02:30 | 1900-01-03 21:00 | 1900-01-03 13:00 | 1900-01-03 09:15 | 1900-01-03 09:15 | 1900-01-03 09:15 | 1900-01-03 09:15

## Totals
Totals and charts
| week1 | week2 | week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | Totals | % Finished
Sprint Planning | 0.29236 | 0.125 | 0.125 | 0.20833 | 0.13194 | 0.11111 | 0.125 | 0.020833 | 0 | 0 | 1899-12-31 03:21
Daily Scrum | 0.069444 | 0.027778 | 0.048611 | 0.048611 | 0.048611 | 0.017361 | 0.017361 | 0 | 0 | 0 | 0.27778
Sprint Review | 0.083333 | 0 | 0 | 0 | 0.020833 | 0 | 0.020833 | 0 | 0 | 0 | 0.125
Sprint Retrospective | 0.083333 | 0 | 0.041667 | 0 | 0 | 0 | 0.020833 | 0 | 0 | 0 | 0.14583
Lectures/Plenary meetings | 0.875 | 0.41667 | 0.4375 | 0.47917 | 0.58333 | 0.27083 | 0.27083 | 0.083333 | 0 | 0 | 1900-01-02 10:00
Sprint Tasks | 0.33333 | #REF! | 0.47917 | 0.375 | 0.4375 | 0.39583 | 0.35417 | 0.5 | 0 | 0 | #REF!
Sprint Task 1.1: Read course material | 0.25 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
Sprint Task 1.2: Feedback on example paper | 0 | 0 | 0.020833 | 0 | 0.125 | 0 | 0 | 0 | 0 | 0 | 0.14583
Sprint Task 1.3: Create schedule | 0.03125 | 0 | 0.020833 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30208
Study | 0 | 0 | 0 | 0.21875 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21875
Sprint Task 1.5: Planning Document | 0.083333 | 0 | 0 | 0.16667 | 0 | 0.083333 | 0 | 0 | 0 | 0 | 0.33333
Sprint Task 1.6: Product backlog | 0 | 0.083333 | 0 | 0.125 | 0.35417 | 0 | 0 | 0 | 0 | 0 | 0.5625
Sprint Task 2.1 designing a conceptual robot | 0 | 0.16667 | 0.20833 | 0 | 0 | 0.29167 | 0 | 0 | 0 | 0 | 0.66667
Sprint Task 2.2 Logic | 0 | 0 | 0 | 0 | 0.020833 | 0 | 0.125 | 0 | 0 | 0 | 0.14583
Sprint Task 2.3: Internet connectivity | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0.16667 | 0 | 0 | 0 | 0.25
Sprint Task 2.4: UML diagrams | 0 | 0 | 0 | 0 | 0 | 0 | 0.3125 | 0 | 0 | 0 | 0.3125
Sprint Task 2.5: Midterm Presentation | 0 | 0 | 0 | 0.25 | 0 | 0 | 0.10417 | 0 | 0 | 0 | 0.35417
Sprint Task 2.6: Midterm video | 0 | 0 | 0 | 0 | 0 | 0 | 0.16667 | 0 | 0 | 0 | 0.16667
Sprint Task 3.1 Intermediate peer review | 0 | 0 | 0 | 0 | 0.03125 | 0 | 0.10417 | 0 | 0 | 0 | 0.13542
Sprint Task 3.2 Acceptance Test Plan | 0.0069444 | 0.0034722 | 0.0034722 | 0.0069444 | 0.010417 | 0.010417 | 0.21875 | 0 | 0 | 0 | 0.26042
Sprint Task 3.3 User Manual | 0.0069444 | 0.020833 | 0.0069444 | 0.0069444 | 0.0069444 | 0.0069444 | 0.020833 | 0 | 0 | 0 | 0.076389
Sprint Task 4.1 App implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0.22917 | 0 | 0 | 0 | 0.22917
Sprint Task 4.2 Final Presentation | 0 | 0 | 0 | 0 | 0 | 0 | 0.041667 | 0 | 0 | 0 | 0.041667
Sprint Task 4.3 Acceptance Test | 0 | 0 | 0 | 0 | 0 | 0 | 0.020833 | 0 | 0 | 0 | 0.020833
Sprint Task 4.4 Gathering and submitting | 0.052083 | 0.03125 | 0.052083 | 0.052083 | 0.03125 | 0 | 0 | 0 | 0 | 0 | 0.21875
Sprint Task: building robot | 0 | 0 | 0 | 0.25 | 0 | 0 | 0.20833 | 0 | 0 | 0 | 0.45833
Sprint Task 4.5: requesting parts | 0 | 0 | 0 | 0 | 0.020833 | 0 | 0 | 0 | 0 | 0 | 0.020833
Belt inspection: | 0 | 0 | 0 | 0 | 0.020833 | 0 | 0 | 0 | 0 | 0 | 0.020833
sprint Task 4.6: Fixing the robot manipulator 3D mesh | 0 | 0 | 0 | 0 | 0.16667 | 0 | 0 | 0 | 0 | 0 | 0.16667
Sprint Task: testing servo | 0 | 0 | 0 | 0 | 0 | 0.041667 | 0 | 0 | 0 | 0 | 0.041667
Sprint Task: building gripper | 0 | 0 | 0 | 0 | 0 | 0.125 | 0 | 0 | 0 | 0 | 0.125
Sprint Task: Building Pusher | 0 | 0 | 0 | 0 | 0 | 0.083333 | 0.041667 | 0 | 0 | 0 | 0.125
Installing SERVOS | 0 | 0 | 0 | 0 | 0 | 0.083333 | 0 | 0 | 0 | 0 | 0.083333
Testing robot functionality | 0 | 0 | 0 | 0 | 0 | 0 | 0.20833 | 0 | 0 | 0 | 0.20833
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| week1 | week2 | week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | Totals
Serkan Efe Durusu | 0.35486 | 0.23958 | 0.24653 | 0.54167 | 0.47917 | 0.34375 | 0.48611 | 0 | 0 | 0 | 1900-01-01 16:36
Celine Zanders | 0.20833 | 0.16667 | 0.22917 | 0.125 | 0.22917 | 0.33333 | 0.15625 | 0 | 0 | 0 | 1899-12-31 10:45
can Işmar | 0.35417 | 0.14583 | 0.20833 | 0.375 | 0.33333 | 0.0625 | 0.4375 | 0.60417 | 0 | 0 | 1900-01-01 12:30
Marios Papalouka | 0.29167 | 0.20833 | 0.25 | 0.375 | 0.25 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 09:00
Metehan Topaç | 0.35417 | 0.3125 | 0.125 | 0.53125 | 0.29167 | 0.33333 | 1899-12-31 04:30 | 0 | 0 | 0 | 1900-01-02 03:15
Ismail Elmasry | 0.45833 | 0.40625 | 0.38542 | 0.48958 | 0.42708 | 0.44792 | 0.51042 | 0 | 0 | 0 | 1900-01-02 03:00
0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| 1900-01-01 00:31 | 1899-12-31 11:30 | 1899-12-31 10:40 | 1900-01-01 10:30 | 1900-01-01 00:15 | 1899-12-31 12:30 | 1900-01-01 18:40 | 0.60417 | 0 | 0 | 1900-01-13 07:06
Formulas:
week1 = SUM(C135:[week1, row above])
Totals = SUM([week1]:[week10])